Table of Contents

# Gemini Full Migration Playbook

Scope: replace all three OpenAI/Anthropic touchpoints (embeddings, main generation LLM, auxiliary LLM) with Google Gemini via Vertex AI. Each piece is swapped, not removed — every capability the system has today is preserved with a Gemini equivalent. After this migration, the only LLM provider in the production data path is Google.

## 1. Executive summary

The migration is structured into five phases: Vertex AI setup, embedding provider swap, generation provider swap, auxiliary LLM swap, and cleanup of the now-unused OpenAI/Anthropic dependencies.

Recommendation: sequence the phases. Phase 1 has the largest blast radius (DB schema + re-embedding); finish and validate it before touching generation. Phases 2 and 3 can be merged into a single sprint after that.

The result is a single-cloud, EU-resident AI stack with no outbound calls to US providers — a meaningful GDPR posture upgrade for tenants processing patient data.

### What changes (and what does not)

| Capability | Today | After migration |
| --- | --- | --- |
| Embeddings (vectors used to retrieve relevant document chunks) | OpenAI text-embedding-3-small (1536 dim) | Gemini text-embedding-005 (768 dim) — still embedding |
| Main generation LLM (writes RAG answers) | Anthropic Claude (Opus class) | Gemini 2.5 Pro — still generating |
| Auxiliary LLM (small helper for tools / structured output) | OpenAI gpt-4o-mini | Gemini 2.5 Flash — still helping |
| RAG architecture (retrieval + generation + caching) | unchanged | unchanged |
| pgvector store + HNSW index | unchanged | unchanged (different column, same shape) |
| gRPC RAG service, FastAPI core-backend, Cloud Run topology | unchanged | unchanged |

## 2. Target state

BEFORE                                AFTER
┌────────────────────────────────────┐  ┌────────────────────────────────────┐
│ Embeddings: OpenAI                 │  │ Embeddings: Vertex AI              │
│   text-embedding-3-small (1536)    │  │   text-embedding-005 (768)         │
│                                    │  │                                    │
│ Generation: Anthropic Claude       │  │ Generation: Vertex AI Gemini       │
│   claude-opus-4.x (US)             │  │   gemini-2.5-pro (europe-west1)    │
│                                    │  │                                    │
│ Aux LLM: OpenAI gpt-4o-mini        │  │ Aux LLM: Vertex AI Gemini          │
│   (agentic RAG, structured output) │  │   gemini-2.5-flash                 │
│                                    │  │                                    │
│ Auth: 2 API keys (OPENAI, ANTHRO)  │  │ Auth: 1 GCP service account        │
│ Egress: cross-Atlantic (US)        │  │ Egress: in-region (EU)             │
│ Sub-processors: Anthropic + OpenAI │  │ Sub-processors: Google only        │
└────────────────────────────────────┘  └────────────────────────────────────┘

## 3. Prerequisites

Before any code is written:

- Vertex AI API enabled on the GCP project (gcloud services enable aiplatform.googleapis.com)

- The Cloud Run runtime service accounts (core-backend-runner@…, rag-service-runner@…) granted roles/aiplatform.user

- Confirmed Vertex AI regional availability for europe-west1: text-embedding-005, gemini-2.5-pro, gemini-2.5-flash — verify on the live Vertex page; quotas may vary by region

- Customer’s GCP billing has Vertex AI enabled and quota raised if backfill volume exceeds default per-minute caps

- An eval set of ~30–50 question/answer pairs from real protocol PDFs to grade quality before/after each phase (Phase 1 needs retrieval-only eval; Phase 2 needs end-to-end eval)

- A staging environment where you can dual-run providers without affecting paying tenants

- Stakeholder sign-off that the Anthropic and OpenAI contracts can be cancelled at the end (the savings only land when you actually stop paying them)

## 4. Phase 0 — Vertex AI setup

Goal: have a working Vertex client in the codebase before changing any runtime path.

### 4.1 Add dependencies

requirements.txt (both core-backend.V4 and rag-service):

google-cloud-aiplatform>=1.71.0
langchain-google-vertexai>=2.0.0

The OpenAI / Anthropic packages stay in requirements.txt until phase 4 — they are still used by the fallback branch of the provider factory.

### 4.2 Add config

app/config.py — new settings:

class Settings(BaseSettings):
    # … existing …
    gcp_project_id: str = ""
    gcp_region: str = "europe-west1"
    embedding_provider: Literal["openai", "vertex"] = "openai"   # flag
    generation_provider: Literal["anthropic", "vertex"] = "anthropic"
    aux_llm_provider: Literal["openai", "vertex"] = "openai"
    vertex_embedding_model: str = "text-embedding-005"
    vertex_generation_model: str = "gemini-2.5-pro"
    vertex_aux_model: str = "gemini-2.5-flash"

### 4.3 IAM grant (one-time)

PROJECT=braided-visitor-484216-i0

for SA in core-backend-runner@$PROJECT.iam.gserviceaccount.com \
          rag-service-runner@$PROJECT.iam.gserviceaccount.com; do
  gcloud projects add-iam-policy-binding $PROJECT \
    --member="serviceAccount:$SA" \
    --role="roles/aiplatform.user"
done

No new secrets. Vertex auth uses Application Default Credentials inherited from the runtime service account on Cloud Run — the SDK auto-discovers it.

### 4.4 Verify connectivity

Add a tiny script scripts/verify_vertex.py:

import asyncio
from langchain_google_vertexai import VertexAIEmbeddings, ChatVertexAI

async def main():
    e = VertexAIEmbeddings(model_name="text-embedding-005",
                            project="…", location="europe-west1")
    v = await asyncio.to_thread(e.embed_query, "hello world")
    print(f"embedding dim: {len(v)}")  # expect 768

    chat = ChatVertexAI(model_name="gemini-2.5-flash",
                        project="…", location="europe-west1")
    r = await chat.ainvoke([("user", "Say hi in one word.")])
    print(r.content)

asyncio.run(main())

Run from a Cloud Run job or locally with gcloud auth application-default login. If both calls succeed, IAM is correct.

## 5. Phase 1 — Embedding provider swap: OpenAI → Vertex

This is the largest phase by far because it touches the database. The plan below mirrors the proven migrations/upgrade_embedding_3072.sql pattern: dual-write → backfill → validate → cutover → drop the obsolete column.

### 5.1 Code changes

#### 5.1.1 Provider-agnostic embedding client

Refactor app/core/openai.py (rename file later to embeddings.py):

def _build_embedding_client():
    s = get_settings()
    if s.embedding_provider == "vertex":
        from langchain_google_vertexai import VertexAIEmbeddings
        return VertexAIEmbeddings(
            model_name=s.vertex_embedding_model,
            project=s.gcp_project_id,
            location=s.gcp_region,
        )
    from langchain_openai import OpenAIEmbeddings
    return OpenAIEmbeddings(
        model=s.embedding_model,
        dimensions=s.embedding_dimensions,
        openai_api_key=s.openai_api_key,
    )

embedding_client = _build_embedding_client()

This is a pure-config swap at runtime. No call site changes — every existing embedding_client.aembed_query(...) works identically.

Mirror the same in rag-service/src/rag_service/clients/openai_client.py (rename to embedding_client.py).

#### 5.1.2 New DB columns

app/models/chunks_docling.py:

embedding_gemini: Mapped[List[float]] = Column(Vector(768), nullable=True)

app/models/semantic_cache.py:

query_embedding_gemini: Mapped[List[float]] = Column(Vector(768), nullable=True)

The system still has embeddings — the new column lives alongside the existing OpenAI one for the duration of the migration so retrieval can use whichever the runtime config selects.

#### 5.1.3 Dual-write at ingest

rag-service/src/rag_service/services/ingestion_service.py:

async def _insert_docling_chunks(self, document_id, document_url, chunks, embeddings):
    # … existing INSERT for `embedding` (1536 OpenAI) …

    if settings.embedding_provider == "vertex":
        # populate the 768 column for new ingestions
        gemini_embeddings = await vertex_client.aembed_documents(
            [c.page_content for c in chunks]
        )
        await self._update_gemini_column(document_id, gemini_embeddings)

This way, every new document written during the migration window has both columns populated. Existing documents need backfill (5.4).

#### 5.1.4 Read-path switch

rag-service/src/rag_service/services/retrieval_service.py and the core-backend mirror — wrap the existing pgvector query in a provider check:

column = "embedding_gemini" if settings.embedding_provider == "vertex" else "embedding"
sql = text(f"""
    SELECT pc.content, pc.page_number, pc.chunk_metadata,
           1 - (pc.{column} <=> ($1)::vector) AS similarity
      FROM document_chunks_docling pc
     WHERE pc.document_id = $2
     ORDER BY pc.{column} <=> ($1)::vector
     LIMIT $3
""")

semantic_cache_service.py — same treatment (column-name switch).

### 5.2 Database migration

New file: migrations/add_gemini_embedding_columns.sql:

SET search_path TO public, extensions;

-- Add the new columns alongside the existing ones (dual-column phase)
ALTER TABLE document_chunks_docling
  ADD COLUMN IF NOT EXISTS embedding_gemini vector(768);

ALTER TABLE semantic_cache_responses
  ADD COLUMN IF NOT EXISTS query_embedding_gemini vector(768);

-- HNSW index on the new column (will be empty until backfill runs;
-- index creation is fast on empty data)
CREATE INDEX IF NOT EXISTS idx_chunks_embedding_gemini_hnsw
  ON document_chunks_docling
  USING hnsw (embedding_gemini vector_cosine_ops)
  WITH (m = 16, ef_construction = 64);

CREATE INDEX IF NOT EXISTS idx_semantic_cache_embedding_gemini_hnsw
  ON semantic_cache_responses
  USING hnsw (query_embedding_gemini vector_cosine_ops)
  WITH (m = 16, ef_construction = 64);

-- Verify
SELECT column_name, data_type, character_maximum_length
  FROM information_schema.columns
 WHERE table_name IN ('document_chunks_docling', 'semantic_cache_responses')
   AND column_name LIKE '%embedding_gemini%';

Apply via DBeaver against the cloud DB (idempotent — safe to re-run). Self-heal block in app/main.py should also be updated to add these columns on app startup for any environment that hasn’t run the SQL.

### 5.3 Reset semantic cache

The semantic cache stores embeddings as keys; mixing OpenAI and Gemini vectors in the same column is meaningless because they live in different latent spaces. Clear the cache so it rebuilds organically against the new vectors:

DELETE FROM semantic_cache_responses;

Brief warm-up cost only — the cache repopulates with normal traffic.

### 5.4 Backfill existing chunks

A one-shot script scripts/backfill_gemini_embeddings.py:

"""Re-embed every existing chunk with Vertex text-embedding-005.

Idempotent: skips chunks that already have embedding_gemini populated.
Resumable: on failure, re-run picks up where it left off.
"""

import asyncio
from sqlalchemy import select, update
from app.db.session import async_session
from app.models.chunks_docling import DocumentChunkDocling
from langchain_google_vertexai import VertexAIEmbeddings

BATCH_SIZE = 100  # tune to Vertex per-minute quota

async def backfill():
    embedder = VertexAIEmbeddings(
        model_name="text-embedding-005",
        project="…",
        location="europe-west1",
    )

    async with async_session() as db:
        while True:
            # Fetch a batch with NULL gemini column
            rows = (await db.execute(
                select(DocumentChunkDocling)
                .where(DocumentChunkDocling.embedding_gemini.is_(None))
                .limit(BATCH_SIZE)
            )).scalars().all()
            if not rows:
                break

            texts = [r.content for r in rows]
            vectors = await asyncio.to_thread(embedder.embed_documents, texts)

            for row, vec in zip(rows, vectors):
                await db.execute(
                    update(DocumentChunkDocling)
                    .where(DocumentChunkDocling.id == row.id)
                    .values(embedding_gemini=vec)
                )
            await db.commit()
            print(f"Backfilled {len(rows)} chunks…")

asyncio.run(backfill())

Run from a Cloud Shell session (or a Cloud Run Job). Larger tenants may need quota raised.

### 5.5 Validation gate

Before flipping embedding_provider=vertex in the read path, run an eval harness that:

- Holds out 30+ question/expected-page pairs per protocol

- Queries with both providers (OpenAI vs Vertex) using the still-dual embedding columns

- Reports recall@5 and recall@20 for each

- Compares cited-page accuracy on a sample of generated answers (this is a retrieval-quality gate, not a generation-quality gate yet — Claude is still generating)

Pass criteria (suggested): - Recall@5 within 5% of the OpenAI baseline - No regression on protocol-specific queries (e.g. inclusion criteria, dosing tables) — these are the queries the FE actually serves

If Vertex underperforms, options: - Increase output_dimensionality to 768 (if you tried 256/512) - Switch to gemini-embedding-001 (3072 native dim, supports MRL down) but be aware it triples vector storage size - Tweak retrieval top_k or rerank cutoffs

### 5.6 Cutover

Single env var flip per environment:

gcloud run services update core-backend-eu \
    --region=europe-west1 \
    --update-env-vars="EMBEDDING_PROVIDER=vertex"

gcloud run services update rag-service-eu \
    --region=europe-west1 \
    --update-env-vars="EMBEDDING_PROVIDER=vertex"

Roll back: flip back to openai. The OpenAI column is still populated. Zero data loss.

### 5.7 Drop the obsolete OpenAI embedding column (deferred to Phase 4)

After 1–2 weeks of stable Vertex operation, the now-unused OpenAI embedding column can be retired:

ALTER TABLE document_chunks_docling DROP COLUMN embedding;
ALTER TABLE document_chunks_docling RENAME COLUMN embedding_gemini TO embedding;
DROP INDEX idx_chunks_embedding_hnsw;
ALTER INDEX idx_chunks_embedding_gemini_hnsw RENAME TO idx_chunks_embedding_hnsw;
-- (same pattern for semantic_cache_responses)

The system still has an embedding column with HNSW index after this — it now holds the Gemini vectors under the same name as before.

## 6. Phase 2 — Generation provider swap: Claude → Gemini 2.5 Pro

This is independent of Phase 1 because generation happens after retrieval — the embeddings used to retrieve are decoupled from the LLM that synthesizes the answer.

### 6.1 Code changes — single service, single class

rag-service/src/rag_service/services/generation_service.py is the only file with Anthropic calls in production (the local doclingRag generation service in core-backend is dev-only). Refactor along provider boundaries:

def _build_generation_client():
    s = get_settings()
    if s.generation_provider == "vertex":
        from langchain_google_vertexai import ChatVertexAI
        return ChatVertexAI(
            model_name=s.vertex_generation_model,
            project=s.gcp_project_id,
            location=s.gcp_region,
            temperature=0.0,
            max_output_tokens=4096,
        )
    from langchain_anthropic import ChatAnthropic
    return ChatAnthropic(
        model=s.anthropic_model,
        anthropic_api_key=s.anthropic_api_key,
        temperature=0.0,
        max_tokens=4096,
    )

Replace direct client.messages.create(...) calls (Anthropic SDK) with langchain_core invocation (or use Vertex SDK directly — pick one).

### 6.2 Prompt adaptation

This is the part that looks small but isn’t. Claude’s strengths (strict JSON adherence, instruction following on long contexts) don’t translate 1:1 to Gemini. Specific prompt elements that need re-validation:

| Claude pattern | Gemini equivalent |
| --- | --- |
| system=[{type:"text", text:"…", cache_control:{type:"ephemeral"}}] (prompt caching) | Vertex AI context caching — different API, separate cachedContents.create call, longer minimum cache duration |
| messages.create with explicit <answer><sources> XML tags | Use Gemini’s structured output (response_schema parameter) — cleaner; emit JSON natively rather than parsing XML |
| system prompt with strict JSON schema instructions | Tighten via response_schema Pydantic model + response_mime_type="application/json" |
| Long context (200k tokens) | Gemini 2.5 Pro supports 2M tokens — context window not a constraint |
| Tool use / function calling | Gemini supports it but the request shape differs — re-test the agentic path if used |

Plan iteration of the prompt against a real eval set.

### 6.3 Validation gate (end-to-end)

Same eval set as Phase 1, but now grading answer quality (not just retrieval). Suggested rubric:

- Faithfulness — does the answer only cite information in the retrieved chunks? (Gemini 2.5 Pro is generally strong here, but verify.)

- Citation accuracy — do the cited page numbers actually contain the claimed information?

- Format compliance — does the JSON validate against the response schema 100% of the time? (This was a quiet strength of Claude; verify Gemini matches.)

- Latency — Gemini 2.5 Pro is typically faster than Claude Opus (1.5–3s vs 5–15s for typical RAG answers). Confirm.

- Cost — Vertex pricing per million tokens vs Anthropic’s. Run on representative traffic for a day to compare.

Pass criteria: ≥95% format compliance, faithfulness on par with Claude on the eval set, no individual question regression > 1 quality grade.

### 6.4 Cutover

gcloud run services update rag-service-eu \
    --region=europe-west1 \
    --update-env-vars="GENERATION_PROVIDER=vertex"

Hot-swap. Roll back via the env var if issues surface.

## 7. Phase 3 — Auxiliary LLM swap: gpt-4o-mini → Gemini 2.5 Flash

gpt-4o-mini is used in the agentic-RAG side path (currently not on the hot path of a typical query, but imported/loaded on app start). Specific call sites:

- app/core/openai.py:39–47 — structured_llm singleton bound to DoclingRagStructuredResponse

- app/core/openai.py:50–54 — general-purpose llm used by tool calls

- app/services/agenticRag/agent.py:13,39 — llm.bind_tools(...) for the agentic flow

- app/services/agenticRag/tools/documents_retrieval_generation_tool.py:138

- app/services/indexing/document_service.py:17,36,353 — legacy non-Docling indexing path with LLM_MODEL_NAME = "gpt-4o-mini"

### 7.1 Decision: port or delete?

The agenticRag and indexing modules may be dead code in production. Verify:

grep -rn "from app.services.agenticRag" app/ --include="*.py"
grep -rn "from app.services.indexing" app/ --include="*.py"

If neither is imported by an active route handler, delete them. That’s the cleanest path. Dead code that imports OpenAI is a compliance hazard (“why does the bundle still ping OpenAI on cold start?”) regardless of runtime behaviour.

If they ARE used, port the structured_llm and llm singletons:

def _build_aux_llm():
    s = get_settings()
    if s.aux_llm_provider == "vertex":
        from langchain_google_vertexai import ChatVertexAI
        return ChatVertexAI(
            model_name=s.vertex_aux_model,  # gemini-2.5-flash
            project=s.gcp_project_id,
            location=s.gcp_region,
            temperature=0.0,
        )
    from langchain_openai import ChatOpenAI
    return ChatOpenAI(model="gpt-4o-mini", api_key=s.openai_api_key, temperature=0.0)

llm = _build_aux_llm()
structured_llm = llm.with_structured_output(DoclingRagStructuredResponse)

with_structured_output works against ChatVertexAI in langchain_google_vertexai>=2.0.0. Verify with a unit test.

### 7.2 Cutover

gcloud run services update core-backend-eu \
    --region=europe-west1 \
    --update-env-vars="AUX_LLM_PROVIDER=vertex"

## 8. Phase 4 — Cleanup of obsolete OpenAI/Anthropic integration

Once all three swaps have been stable for 1–2 weeks. This phase removes the now-unused OpenAI and Anthropic SDKs, API keys, and dual-provider plumbing — none of which are still serving traffic. Functionality is unchanged; the system runs purely on Gemini.

### 8.1 Drop dual-provider code

- Delete the _build_*_client factories’ OpenAI/Anthropic branches

- Remove the embedding_provider / generation_provider / aux_llm_provider settings (hardcode Vertex)

- Drop the (now-empty) OpenAI embedding column (rename embedding_gemini → embedding)

### 8.2 Drop the obsolete SDK dependencies

requirements.txt:

- openai
- langchain-openai
- anthropic
- langchain-anthropic
+ # already added in Phase 0:
+ # google-cloud-aiplatform
+ # langchain-google-vertexai

### 8.3 Revoke API keys

In GCP Secret Manager:

gcloud secrets versions destroy latest --secret=OPENAI_API_KEY
gcloud secrets versions destroy latest --secret=ANTHROPIC_API_KEY
# (or just delete the secrets entirely)
gcloud secrets delete OPENAI_API_KEY --quiet
gcloud secrets delete ANTHROPIC_API_KEY --quiet

Cancel the OpenAI and Anthropic billing accounts. Notify procurement.

### 8.4 Update sub-processor register

Drop OpenAI and Anthropic from the customer’s sub-processor list (since neither is still used). Update the customer’s privacy notice if it named those providers. This is a GDPR-relevant change that must be communicated to data subjects per Article 28(2).

## 9. Validation strategy summary

| Gate | Criterion | Block Phase X if fails |
| --- | --- | --- |
| Phase 1 — embedding provider swap | Recall@5 within 5% of OpenAI baseline; no individual protocol query regression | Phase 1 cutover |
| Phase 2 — generation provider swap | ≥95% structured-output format compliance; faithfulness on par; latency ≤ baseline | Phase 2 cutover |
| Phase 3 — aux LLM swap | All affected unit tests pass; agentic flow (if not deleted) returns correctly-shaped tool calls | Phase 3 cutover |
| Phase 4 — cleanup | No errors in 1-week post-cutover monitoring; no OpenAI/Anthropic calls in logs | Drop deps + keys |

## 10. Rollback plan per phase

| Phase | If issue surfaces | Rollback action | Recovery time |
| --- | --- | --- | --- |
| 1 | Vertex retrieval recall too low | Flip EMBEDDING_PROVIDER=openai env var on both Cloud Run services | < 1 minute |
| 2 | Gemini answer quality regresses | Flip GENERATION_PROVIDER=anthropic | < 1 minute |
| 3 | Aux LLM breaks an agent | Flip AUX_LLM_PROVIDER=openai | < 1 minute |
| 4 (post-cleanup) | Vertex outage > 30 min | Cannot roll back — providers gone. Hard dependency on Google. | n/a — risk to accept |

This is why Phase 4 cleanup waits 1–2 weeks. Until cleanup, every phase is reversible by toggling an env var.

## 11. Risk register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Vertex retrieval quality < OpenAI on niche medical queries | Medium | High (RAG returns “no info” more often) | Eval set + Phase 1 gate; fall back to gemini-embedding-001 (3072 dim) if 768 underperforms |
| Gemini structured-output less reliable than Claude | Low | Medium (downstream JSON parse errors) | Use response_schema Pydantic model — strict schema; validation gate at 95% |
| Vertex regional quota hit during backfill | Medium | Low (slower backfill) | Run backfill off-hours; request quota raise pre-emptively |
| Anthropic prompt caching savings lost; Vertex caching less mature | Medium | Low–Medium ($) | Measure post-cutover cost for 1 week; consider Vertex cachedContents API |
| Gemini 2.5 Pro changes pricing or model availability | Low | Low | Standard model-deprecation drill — same risk we accepted with Anthropic/OpenAI |
| Single-cloud lock-in | Inherent | Medium | This was already the architectural direction (GCP-native deployment). Documented trade-off. |
| Customer rejects Google as sole AI sub-processor | Low | High (deal block) | Surface during sales discovery; some EU customers prefer Google over US-only providers |

## 12. Files touched (summary)

| File | Change |
| --- | --- |
| app/config.py | new settings (provider flags, GCP project) |
| app/core/openai.py → embeddings.py | factory pattern |
| rag-service/src/rag_service/clients/embedding_client.py | mirror |
| rag-service/src/rag_service/services/generation_service.py | factory + prompt adapt |
| rag-service/src/rag_service/services/ingestion_service.py | dual-write |
| rag-service/src/rag_service/services/retrieval_service.py | column switch |
| app/services/cache/semantic_cache_service.py | column switch |
| app/services/doclingRag/rag_retrieval_service.py | column switch |
| app/services/agenticRag/* | port or delete |
| app/services/indexing/document_service.py | port or delete |
| app/models/chunks_docling.py | new column |
| app/models/semantic_cache.py | new column |
| app/main.py | self-heal block for new columns |
| migrations/add_gemini_embedding_columns.sql | new file |
| scripts/backfill_gemini_embeddings.py | new file |
| scripts/verify_vertex.py | new sanity script |
| requirements.txt (both repos) | add Vertex; drop OpenAI/Anthropic in cleanup |
| .github/workflows/deploy-cloud-run.yml (both repos) | new env vars; drop API key secrets in cleanup |

The migration is approximately 80% configuration / operations / validation, ~20% code.

## 13. One-line answer for stakeholders

“Full migration to Google Gemini results in zero OpenAI and zero Anthropic dependencies, with all AI traffic remaining in europe-west1, and the customer’s sub-processor list shrinking to a single name — Google. Each phase is independently reversible until final cleanup, so risk is bounded throughout. Every capability the system has today is preserved with a Gemini equivalent.”

## Appendix A — Useful commands

# Enable Vertex AI on the project
gcloud services enable aiplatform.googleapis.com \
    --project=braided-visitor-484216-i0

# Grant the Cloud Run runtime SA permission to call Vertex
gcloud projects add-iam-policy-binding braided-visitor-484216-i0 \
    --member="serviceAccount:core-backend-runner@braided-visitor-484216-i0.iam.gserviceaccount.com" \
    --role="roles/aiplatform.user"

# List Vertex AI models available in europe-west1
gcloud ai models list --region=europe-west1

# Smoke-test the embedding API from a Cloud Shell
curl -X POST -H "Authorization: Bearer $(gcloud auth print-access-token)" \
  -H "Content-Type: application/json" \
  "https://europe-west1-aiplatform.googleapis.com/v1/projects/braided-visitor-484216-i0/locations/europe-west1/publishers/google/models/text-embedding-005:predict" \
  -d '{"instances":[{"content":"hello world"}]}'

# Check current Vertex quotas in the project
gcloud compute project-info describe --project=braided-visitor-484216-i0 \
    --format='get(quotas)' | grep -i aiplatform

## Appendix B — What NOT to do

- ❌ Don’t drop the OpenAI embedding column before the new column is fully populated and validated. Once the old column is gone, rollback is no longer free.

- ❌ Don’t mix OpenAI and Vertex embeddings in the same pgvector column — different latent spaces, cosine similarity becomes noise.

- ❌ Don’t swap Claude for Gemini and embeddings for Vertex in the same deploy. Two big variables changing at once = no clean diagnosis if quality drops.

- ❌ Don’t assume Anthropic-style prompt caching works on Vertex out of the box — Vertex cachedContents is a different API with a different cost model. Re-validate cost savings after migration.

- ❌ Don’t skip the eval set. It’s the only thing that catches silent quality regressions in retrieval and generation. Build it before Phase 1 even starts.